## Action Items
PO Requisition Agent — Action Items
# | Category | Action Item | Details | Priority | Owner | Due Date | Status | Source
1 | Data Quality | Fix upstream ERP export — Tax Amount column | Source system exports Total Amount as post-tax but does not populate Tax Amount ($). Agent validation rule now handles this (see validator.py), but root fix belongs in the ERP export query/template. | Critical | Finance Ops / ERP Admin | 2026-06-15 | Open | reports/validation_failure_analysis.md
2 | Data Quality | Re-run agent after ERP export fix and confirm 0 errors | Once Tax Amount ($) is correctly exported, re-run against a fresh dataset and verify the 75% failure rate drops to 0. | High | Finance Ops | 2026-06-20 | Open | reports/run_summary_20260529.md
3 | Approval Queue | VP review — 33 POs pending sign-off ($2.9M spend) | 33 POs routed to VP Approval tier are awaiting review. Largest: PO-2024-0150 ($190,987), PO-2025-0007 ($189,729), PO-2024-0136 ($186,326). | Critical | VP / Procurement Lead | 2026-06-05 | Open | outputs/PO_Processed_20260529_224746.xlsx — Approval Queue sheet
4 | Approval Queue | Manager review — 14 POs pending sign-off ($200K spend) | 14 POs in the Manager Approval tier ($5K–$25K). Should be cleared before VP queue. | High | Department Managers | 2026-06-05 | Open | outputs/PO_Processed_20260529_224746.xlsx — Approval Queue sheet
5 | Vendor Risk | Investigate SecureNet Systems vendor concentration | SecureNet Systems represents 20.1% of run spend ($626,438 of $3.1M), marginally above the 20% concentration threshold. Review IT Hardware sourcing strategy and qualify at least one alternative supplier. | High | Procurement / IT Lead | 2026-06-30 | Open | reports/vendor_concentration_watch.md
6 | Vendor Risk | Verify preferred-supplier status for all vendors in run | Cross-reference vendor_allowlist.csv against POs in the run. Flag any Vendor IDs not on the approved list. | Medium | Procurement | 2026-06-30 | Open | config/vendor_allowlist.csv
7 | Stale POs | Triage 62 POs with past-due Needed By dates | 62 POs have a Needed By Date in the past. Oldest: PO-2025-0183 (due 2024-02-11). Determine: retroactive booking, stale requisition, or legitimate delay. | High | Finance Ops / Dept Owners | 2026-06-10 | Open | outputs/agent_log_20260529_224746.txt — Past-due section
8 | Stale POs | Cancel or close confirmed stale requisitions | After triage (#7), cancel POs confirmed as stale to keep the register clean. Update Status to 'Closed' in the source system. | Medium | Finance Ops | 2026-06-20 | Open | Dependent on #7
9 | Compliance | Audit high-volume requesters for split-order activity | 10 requesters exceeded the 10-PO threshold. Top: Monica Shaw (24), Patricia Dunn (23), Robert Nash (23). Spot-check for PO splitting to avoid approval thresholds. | High | Internal Audit / Finance | 2026-06-30 | Open | outputs/agent_log_20260529_224746.txt — Anomalies section
10 | Compliance | Review high-value POs > $100K (10 flagged) | 10 POs exceed $100K — all correctly routed to VP tier. Confirm each has a valid business justification on file before VP sign-off. | High | VP / Finance | 2026-06-05 | Open | outputs/agent_log_20260529_224746.txt — Anomalies section
11 | Agent / Code | Update CLAUDE.md validation rule to reflect tax-aware formula | The STEP 2 validation spec still documents the old rule (Total = Qty × Unit Price). Update to: Total Amount ≈ (Qty × Unit Price) + Tax Amount. | Medium | Engineering | 2026-06-07 | Open | CLAUDE.md — STEP 2 / Business Rules Reference
12 | Agent / Code | Bump agent version to 1.1.0 after validation fix | validator.py was patched (tax-aware check). Update src/version.py from 1.0.0 → 1.1.0 and add a CHANGELOG entry. | Low | Engineering | 2026-06-07 | Open | src/version.py, CHANGELOG.md
13 | Agent / Code | Add fixture_edge_cases test for tax-inclusive totals | tests/fixtures/fixture_edge_cases.xlsx does not yet cover the tax-included total scenario. Add a row with Tax Amount ($) > 0 to confirm the new rule passes. | Medium | Engineering | 2026-06-14 | Open | tests/fixtures/fixture_edge_cases.xlsx
14 | Documentation | Write docs/RUNBOOK.md | Step-by-step ops guide: how to drop a new file, what to do on error, how to re-run, how to read the outputs. Recommended in initial repo audit. | Medium | Engineering / Finance Ops | 2026-06-21 | Open | docs/ folder
15 | Documentation | Write docs/FIELD_GLOSSARY.md | Define every input column: type, format, business meaning, and validation rule. Critical for new data providers. | Low | Engineering | 2026-06-28 | Open | schemas/po_input_schema.json
16 | CI / DevOps | Confirm CI pipeline passes on GitHub Actions | ci.yml was pushed but not yet verified green. Check Actions tab after next push and fix any environment issues (Python path, openpyxl version). | High | Engineering | 2026-06-07 | In Progress | .github/workflows/ci.yml
17 | CI / DevOps | Add test coverage for validator.py tax-aware rule | test_validator.py should have at least one test for the updated total amount check (with and without Tax Amount). Ensures the fix doesn't regress. | Medium | Engineering | 2026-06-14 | Open | tests/test_validator.py

## Summary
Action Items Summary
Status | Count |  | Priority | Count
Open |  |  | Critical
In Progress |  |  | High
Done |  |  | Medium
Blocked |  |  | Low
Total |  |  | Total
Category Breakdown
Category | Total Items | Open | Done
Agent / Code
Approval Queue
CI / DevOps
Compliance
Data Quality
Documentation
Stale POs
Vendor Risk